## Sheet1
OpenCart Demo – QA Summary Report
Document Name: OpenCart Demo – QA Summary Report
Document Owner: Afrina Riya
Date of Creation: 07-Apr-2026
Date of Review: 07-Apr-2026
Project Overview
Application: OpenCart Demo (demo.opencart.com)
Test Types: Manual UI · REST API · Browser DevTools · Database
Tester: Afrina Riya
Overall Test Scorecard
Metric | Count
Total UI Test Cases | 68
Passed | 57
Failed | 9
Not Applicable | 2
Total Bugs Found | 25
Functional Bugs | 11
UI Bugs | 14
Total Test Scenarios | 45
UI Test Results by Module
Module | Total | Pass | Fail | Pass Rate | Test Case IDs
Login & Authentication | 12 | 10 | 2 | 83% | TC_UI_01–TC_UI_12
Registration | 8 | 6 | 2 | 75% | TC_UI_13–TC_UI_20
Search | 8 | 8 | 0 | 100% | TC_UI_21–TC_UI_28
Product & Detail | 8 | 7 | 1 | 87% | TC_UI_29–TC_UI_36
Shopping Cart | 8 | 8 | 0 | 100% | TC_UI_37–TC_UI_44
Checkout | 8 | 3 | 5 | 37% ⚠️
My Account | 8 | 8 | 0 | 100%
Homepage & Navigation | 8 | 7 | 1 | 87%
TOTAL | 68 | 57 | 9 | 83%
Bug Report Summary
Severity | Count | Description
Critical | 3 | Blocks core functionality — must fix immediately
Major | 4 | Core feature broken; fix before release
Moderate | 6 | Partial functionality issue; fix in next sprint
Minor | 8 | Low impact; can be deferred
Trivial | 4 | Cosmetic issues only
Total Bugs: 25
Functional: 11
UI: 14
API & Database Test Results
Testing Type | Total | Pass | Fail | Pass Rate
Postman (reqres.in) | 8 | 8 | 0 | 100%
DevTools (OpenCart) | 3 | 3 | 0 | 100%
Database (SQL Queries) | 6 | 5 | 1 | 83%
Test Scenario Coverage
Type | Count
UI Scenarios | 28
API Scenarios | 8
DevTools Scenarios | 3
DB Scenarios | 6
Total | 45
QA Remarks & Observations
Passed:
Majority of UI test cases passed successfully
Core modules (Search, Cart, My Account) are stable
All API tests via Postman (reqres.in) passed
OpenCart API routes observed via DevTools returned expected responses
Failed / Issues Identified:
Checkout module has highest failure rate — orders cannot be placed due to stock error
Session timeout not enforced (security concern)
Out-of-stock products can be added to cart (critical issue)
Database validation failed for oc_order table (order not recorded correctly)
Not Applicable / Missing Features:
"Remember Me" option not available
"Confirm Password" field missing in registration
UI Concerns:
Multiple responsiveness issues on mobile and tablet devices
Minor layout and usability inconsistencies observed
✅ Final Verdict
The application is partially stable, but critical issues in Checkout, Registration validation, and data integrity must be fixed before production use.